## Product roadmap
Products | January |  |  |  |  | February |  |  |  |  | March
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3
Users
User Management
UI
Missions
Mission Management
User Interaction
Progress engine
XP system
Rewards
Achievements
Quality of life
UI
QoL features
Data related
UX
Testing
Tests
Login/Register UI
User Database
Login/Register Functionality
Mission UI
Mission Database
XP Implementation
Navigation Logic
Profile Screen UI
Level implementation
Custom Icons
Reward redemption
UI Themes
Achievement system
Profile Personalization
Streak System
Statistics Screen
Mission Editor
Export Progress
Multiple Profile Support
Sound Effects
End of Iteration 1:
Desktop app
Iteration 2:
Mobile app
Login/Register UI
Profile Screen UI
Mission UI
GPS Integration
QR-code Scanner
Geofence trigers
Push Notifications
Physical Rewards Shipping Integration
End of Iteration 2:
Mobile app
Iteration 3:
Optimizations and Social
Guilds and Social UI
Guilds and Social Functionality
Local business discounts and advertisements
Custom User-Contributed Content
Iteration 1:
Desktop app
Smart Watch Sync
Language and Region Localization
Smoke Tests
Regression Tests
Persistence Edge Tests
Full Regression Tests
End of Iteration 3:
Optimizations and Social